## Index
Patch missing in our environment
Patch present in our environment
Patch can be ignored
Patch already analyzed earlier in the PPA
Customer Name | Tri-Arrows Aluminum Inc.
Instance Name | DEV
Task Description | 12.2 Critical Patch Update (RITM0080064)
DB Outage | 3 hrs
ERP Outage | 2 Hrs
Total Outage | 5 Hrs
Task number
patch location | /backup/OCT_CPU_2025/
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)
Not Applied
Applied

## DB
Current Database Version |  |  | 19.26.0.0.0
DATABASE PATCH SET UPDATE 19c
|  | Patch Number | Description | Size
|  | Patch 38273558 | Combo of OJVM Component Release Update 19.29.0.0.251021 + Grid Infrastructure Oct 2025 Release Update 19.29.0.0.251021
Patch 38298204 - Database Grid Infrastructure Oct 2025 Release Update 19.29.0.0.251021
Patch 38194382 - Oracle JavaVM Component Release Update 19.29.0.0.251021
Patch Pre-Installation Instructions
i. Compile invalid objects and take invalids count. ii. Take the DB_HOME backup. iii. Take cold snap backup. iv. Create the restore point. SQL> shut immediate; SQL> startup mount; SQL> create restore point before_patching_PSU_OCT2025 guarantee flashback database; SQL> alter database open; iv. Take Components status: ------------------------- col COMP_ID for a15 col COMP_NAME for a36 set lines 300 col VERSION for a18 set pages 8000 select COMP_ID,COMP_NAME,VERSION,STATUS from dba_registry; SQL> select patch_id, version, status, bundle_id, bundle_series from dba_registry_sqlpatch;
Patch Installation Instructions
Analyze: --------------------- As the Root user: /us9101/app/oracle/product/19.3/OPatch/opatchauto apply /backup/JULY_CPU_2025/DB/37952382/37957391 -oh /us9101/app/oracle/product/19.3 -analyze As Root user: /us1101/app/oracle/product/19.3.0.0/dbhome_1/OPatch/opatchauto apply /backup/JULY_CPU_2025/DB/37952382/37957391 -oh /us1101/app/oracle/product/19.3.0.0/dbhome_1 -analyze Apply: ------- /us9101/app/oracle/product/19.3/OPatch/opatchauto apply /backup/JULY_CPU_2025/DB/37952382/37957391 -oh /us9101/app/oracle/product/19.3 /us1101/app/oracle/product/19.3.0.0/dbhome_1/OPatch/opatchauto apply /backup/JULY_CPU_2025/DB/37952382/37957391 -oh /us1101/app/oracle/product/19.3.0.0/dbhome_1 OJVM Patches ( Apply as oracle user): -------------------------------------- Check Conflicts: cd /backup/JULY_CPU_2025/DB/37952382/37847857 $ORACLE_HOME/OPatch/opatch prereq CheckConflictAgainstOHWithDetail -ph ./ Apply OJVM patches: -------------------- cd /backup/JULY_CPU_2025/DB/37952382/37847857 $ORACLE_HOME/OPatch/opatch apply
Patch Post Installation Instructions
Post Steps: --------------- shutdown immediate startup upgrade; alter pluggable database all open upgrade; exit cd $ORACLE_HOME/OPatch ./datapatch -verbose connect / as sysdba shutdown immediate startup @$ORACLE_HOME/rdbms/admin/utlrp.sql
Conflict Patch Information

## JRE
JRE Update on Database
JRE 8 Update 471: Patch 38434594
Database Node 1
$ cd $ORACLE_HOME/appsutil
$ mv jre jre_old
$ cp -r /backup/OCT_CPU_2025/DB/JRE/jre .
Run autoconfig
$ cd $ORACLE_HOME/appsutil/scripts/context_name
./adautocfg.sh

## EBS
Applied
Not Applied
EBS Version |  |  |  | 12.2.13
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)
Estimated Outage Time
2 hrs
EBS Patch Details
| Patch Number | Prerequsites1 | Post steps | Patch Description | Size | Outage Required | NLS
| 38298685 | 12.2.3 R12.AD.C.delta.15 R12.TXK.C.delta.15 | Post steps | Patch 38298685: ORACLE APPLICATIONS RELEASE 12.2: CPU PATCH FOR OCTOBER 2025 | 47.0 MB |  | NA
| 38261427 | 12.2.3 R12.AD.C.delta.15 R12.ATG_PF.C.delta.12 R12.TXK.C.delta.15 |  | Patch 38261427: 12.2.13 CONSOLIDATED PATCH FOR OCTOBER CPU 2025 FIXES FOR FWK | 20.0 MB |  | NA
| 37450688 | 12.2.3 R12.AD.C.delta.8 R12.TXK.C.delta.8 |  | Patch 37450688: Fix for Bug 37450688 | 7.2 MB |  | NA
| 38180394 |  |  | Patch 38180394: Extension of APR CPU 2025 Fix | 79.9 KB |  | NA
| 38510732 |  |  | Patch 38510732: Fix for Bug 38510732 | 8.3 MB |  | NA
| 36589745 |  |  | Patch 36589745: Fix for Bug 36589745 | 16.5 KB |  | NA
| 36097561 |  |  | Patch 36097561: Fix for Bug 36097561 | 53.9 KB |  | NA
Post Patching Instructions
Run ETCC & ECPU on Application and make sure no patches are reported.
Reference Notes
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post-install Tasks For 12.0.X / 12.1.X patches, you must complete the tasks in this section before starting up Application tier services. For 12.2.X patches, you may complete the tasks in this section at any time after the update, without taking any services or users offline. Instructions for Patching AutoConfig on Database tier [required]After applying this patch, update all Database Tier Nodes with the code level provided by this patch, by performing the following steps : 1. On the Application Tier (as the APPLMGR user): . Run AutoConfig on the RUN file system. Note: Customers using the AutoConfig Customizations feature must merge any customizations with the AutoConfig templates provided via this patch before running AutoConfig. For exact details on how to run Autoconfig, please refer to the Oracle E-Business Suite Setup Guide for Release 12.2. . Source the environment variables for Oracle Applications UNIX: . ./<APPL_TOP>/APPS<CONTEXT_NAME>.env Windows: <APPL_TOP>\envshell<CONTEXT_NAME>.cmd . Execute admkappsutil.pl utility to create the file appsutil.zip perl <AD_TOP>/bin/admkappsutil.pl This will create appsutil.zip in <INST_TOP>/admin/out Note: For exact details on how to run Autoconfig and how to create appsutil.zip, please refer to the Oracle E-Business Suite Setup Guide for Release 12.2. 2. On the Database Tier (as the ORACLE user): . Source the environment variables for RDBMS ORACLE_HOME UNIX: cd <RDBMS ORACLE_HOME> . ./<RDBMS ORACLE_HOME>/<CONTEXT_NAME>.env Windows: <RDBMS ORACLE_HOME>\<CONTEXT_NAME>.cmd . Copy or FTP the appsutil.zip file to the <RDBMS ORACLE_HOME> . Uncompress appsutil.zip under the <RDBMS ORACLE_HOME> cd <ORACLE_HOME> unzip -o appsutil.zip . Run AutoConfig on the <RDBMS ORACLE_HOME> Note: Please refer to the Oracle E-Business Suite Setup Guide for Release 12.2 for more details.

## 10.1.2 Home
Forms Home Version | 10.1.2.3
Oracle Fusion Middleware 10.1.2.3 |  |  | Estimated Outage Time
10.1.2.3.0
| 26825525 | MERGE REQUEST ON TOP OF 10.1.2.3.2PSU FOR BUGS 25768948 1770039 25990479 | Applied as part of 32922089
ETCC reported | 38429205 | MERGE REQUEST ON TOP OF 10.1.2.3.2PSU FOR BUGS 32922089 37719046 | Not Applied
Reference Notes
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)

## FMW_WebTier
FMW Web Tier
Estimated Outage Time
Oracle Fusion Middleware 11.1.1.9 OHS - Web Tier Home
Patch Number | Patch Description | Size |  | Comment
Patch 35540062 | OHS 11.1.1.9.0 SPU FOR JULCPU2023 (Patch) | 3.9 MB
Reference Notes
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)

## FMW_WebCommon
FMW Oracle Common
Estimated Outage Time
Oracle Product | Patch | Instructions |  | Size
Oracle Fusion Middleware 11.1.1.9 OHS - Common Home | p34330735_111190_Generic.zip |  | Already Applied | 106.4 MB
ETCC reported | 38059622 | Fix for Bug 38059622 | 1.2 MB
ETCC reported | 31973206 | Fix for Bug 31973206 | 173.6 KB
ETCC reported | 38030906
Reference Notes
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)

## Weblogic
Weblogic Patches
Patch Number | Special Instructions | Size | Comment
13845626(4HID) | 13845626 version 10.3.6.0.250715 WLSPSU (4HID) |  | Applied
PG6B (37927515) | WLS Patch Set Update 10.3.6.0.250715 |  | Applied
Patch 35476084 (KMHV) | ADR FOR WEBLOGIC SERVER 10.3.6.0 CPU OCT 2023 |  | Applied
Reference Notes
Oracle E-Business Suite Release 12.2 Critical Patch Update Availability Document (October 2025) (Doc ID 3102287.1)

## JDK& JRE APPS
Task
Old version
JDK 7 Update 481 Restricted: Patch 38434612
upgrade common_top
Oracle JDK 7 Update 461 | $ cd $COMMON_TOP/util/ $ mv jdk32 jdk32_bkp; mv jdk64 jdk64_bkp $ /* Install the latest JDK 7.0 Update here*/ $ cp -r /backup/OCT_CPU_2025/EBS/JDK/JDK_32/jdk32 jdk32 $ cp -r /backup/OCT_CPU_2025/EBS/JDK/JDK_64/jdk64 jdk64
upgrade FMW Home
$ cd $FMW_HOME/webtier $ mv jdk jdk_old $ cp -r /backup/OCT_CPU_2025/EBS/JDK/JDK_64/jdk64 jdk
upgrade 10g home
$ cd $ORACLE_HOME $ mv jdk jdk_old $ cp -r /backup/OCT_CPU_2025/EBS/JDK/JDK_32/jdk32 jdk
Validation
$ $ADJVAPRG -version $ echo $CLASSPATH $ $AFJVAPRG -version $ echo $AF_CLASSPATH
JRE on Applications (Oracle Java Runtime Environment JRE 8 Update 471) -
JRE 8 Update 471: Patch 38434594 (public) (windows 64 bit)
JRE 8 Update 471: Patch 38434594 | cd /backup/OCT_CPU_2025/EBS/JRE ls -ltr j2se18471.exe cp -rp j2se18471.exe $COMMON_TOP/webapps/oacore/util/javaplugin/ txkSetPlugin.sh 18471 dyn
Old version

## Play Book
| Task Number | Person | Downtime | NDBB | BETA | NUAT | NPRDCN
1 | Prep Activities
2 | Create COF documents for snapshot backup and get those uploaded to respective Tasks
3 | Clean old weblogic/ohs logs in run/patch fs
4 | Start Time - Client Communication
5 | Start Adop fs_clone one day before start of activity
6 | Start adop prepare 16 hours before start fo activity
7 | Prereq for application patches
8 | 1. Instructions for Running AD Grants [required] 1. Create $ORACLE_HOME/appsutil/admin on database server. 2. Compare version of adgrants.sql in $APPL_TOP/admin to version in patch directory. 3. Copy whichever is the higher version of adgrants.sql to $ORACLE_HOME/appsutil/admin. 4. Set environment to point to ORACLE_HOME on the database server. Note: If the database is CDB-PDB enabled, source using these steps. UNIX: 4.1 $ source $ORACLE_HOME/<cdb-name>_<host-name>.env 4.2 $ export ORACLE_PDB_SID=<pdb-name> 5. Run the adgrants.sql script using SQL*Plus: UNIX: $ sqlplus /nolog SQL> @$ORACLE_HOME/appsutil/admin/adgrants.sql <APPS schema name>
9 | Apply application patches
10 | Take Invalid Objects & Check components status
11 | Application Patches
12 | { echo $APPS_PWD ; echo $SYSTEM_PWD ; echo $WLS_PWD ; } ¦ adop phase=apply patches= patchtop=/ADMIN/patches/JUL_2023/EBS
13 | Execute steps in JDK, FMW_WebCommon, FMW_WebTier, 10.1.2 Home tab on patch fs - (Wblogic Patches already applies ,Kindly validate)
14 | Finalize
15 | Run adop finalize
16 | Quality check of all applied patches
17 | General Steps (Before Shutdown)
18 | Start Time - Client Communication
19 | Put Nagios targets on downtime (silence Nagios alerts)
20 | Put Scheduled CM Jobs on hold
21 | Get Initial List of Invalid Objects
22 | Put Scheduled Backups on hold
23 | Shutdown Environment & Take Backup
24 | Take a list of running concurrent requests
25 | Shutdown EBS Applications
26 | Shutdown EBS DB
27 | Obtain Cold Snapshot Backup per COF( For EBS & DB )
28 | Ensure we have taken necessary custom code backup
29 | Complete the online patching cycle
30 | Start admin server on application
31 | adop phase=cutover mtrestart=no
32 | Post cutover steps
33 | 1.1. On the Application Tier (as the APPLMGR user): . Run AutoConfig on the RUN file system. Note: Customers using the AutoConfig Customizations feature must merge any customizations with the AutoConfig templates provided via this patch before running AutoConfig. For exact details on how to run Autoconfig, please refer to the Oracle E-Business Suite Setup Guide for Release 12.2. . Source the environment variables for Oracle Applications UNIX: . ./<APPL_TOP>/APPS<CONTEXT_NAME>.env 1.2. Execute admkappsutil.pl utility to create the file appsutil.zip perl <AD_TOP>/bin/admkappsutil.pl This will create appsutil.zip in <INST_TOP>/admin/out Note: For exact details on how to run Autoconfig and how to create appsutil.zip, please refer to the Oracle E-Business Suite Setup Guide for Release 12.2. 1.3. On the Database Tier (as the ORACLE user): . Source the environment variables for RDBMS ORACLE_HOME UNIX: cd <RDBMS ORACLE_HOME> . ./<RDBMS ORACLE_HOME>/<CONTEXT_NAME>.env Windows: <RDBMS ORACLE_HOME>\<CONTEXT_NAME>.cmd . Copy or FTP the appsutil.zip file to the <RDBMS ORACLE_HOME> . Uncompress appsutil.zip under the <RDBMS ORACLE_HOME> cd <ORACLE_HOME> unzip -o appsutil.zip . Run AutoConfig on the <RDBMS ORACLE_HOME>
34 | Apply DB patches, follow instruction from tab DB
35 | Post DB Patches
36 | % sqlplus /nolog SQL> Connect / as sysdba SQL> startup SQL> quit % cd $ORACLE_HOME/Opatch % ./datapatch -verbose
37 | Update Database Tier to Latest Code Create appsutil.zip and copy to DB Node and run autoconfiig Run below in apps node to create appsutil.zip perl $AD_TOP/bin/admkappsutil.pl Then take backup of appsutil directory and copy file it to DB server on $ORACLE_HOME location. Unzip –o appsutil.zip and run autoconfig.
38 | Sanity Checks
39 | Start application services
40 | Compare post invalids
41 | Check Concurrent Managers, OPP, Workflow
42 | Validate all services and customizations
44 | Prepare QA checks documents and send mail to customer
45 | Synchronize Run and Patch File Systems
46 | Run fs_clone to synchronize the PATCH file system with RUN file system